## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
PROJECT TITLE
Company name | ProtoTAU |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead | Christine Koppel
Project Start Date: | 2023-10-03 |  |  |  |  | October | [27 empty] | November
Scrolling Increment: | 4 | time axis 2023-10-07 to 2023-12-01
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2023-10-07 to 2023-12-01
Initial Study and Equipment Evaluation
First Most Important Meeting | On Track |  | 75% | 2023-10-09 | 1
Task assignment and Delegation | High Risk |  | 0% | 2023-10-09 | 5
Inter-team communication and managment of the project | Med Risk |  | 50% | 2023-10-06 | 13
Testing the donated motor | High Risk |  | 25% | 2023-10-16 | 5
Taking in new ideas into the design. | Low Risk |  | 0% | 2023-10-09 | 25
Finalising the Electronics Files and Ordering
KiCAD Schematic Finished | High Risk |  | 80% | 2023-10-15 | 20
KiCAD Chosen Component List Finished | High Risk |  | 80% | 2023-10-17 | 18
KiCAD Gerber File Finished | High Risk |  | 60% | 2023-11-01 | 8
Data and Telemetry Basis | Med Risk |  | 33% | 2023-10-12 | 30
Testing of the sensors (raw data) | Med Risk |  | 0% | 2023-10-13 | 20
Ordering of the components and assembly
Ordering of the PCB from the gerber output | High Risk |  | 0% | 2023-11-11 | 3
Assembly of the components | High Risk |  | 25% | 2023-11-14 | 10
Troubleshooting | Med Risk |  | 0% | 2023-11-14 | 15
Testing of the designed components | High Risk |  | 0% | 2023-11-24 | 3
Data and Telemetry from the designed system. | Med Risk |  | 0% | 2023-11-27 | 10
Testing in the Vehicle
Assembly of the design into the vehicle. | High Risk |  | 0% | 2023-12-02 | 15
Communication check-up with the vehicle | Med Risk |  | 0% | 2024-01-30 | 10
Testing | High Risk |  | 0% | 2024-02-06 | 30
Finishing touches | Low Risk |  | 0% | 2024-02-13 | 30
To add more data, Insert new rows ABOVE this one
Formulas:
ProtoTAU = IFERROR(IF(MIN(Milestones4352[Start])=0,TODAY(),B11(Milestones4352[Start])),TODAY())

## Dark
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2023-10-03 |  |  |  |  | October | [27 empty] | November
Scrolling Increment: | 1 | time axis 2023-10-04 to 2023-11-28
Milestone description | Category | Assigned to | Progress | Start | Days | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T
TITLE 1
Task 1 | Goal | Name | 25% | 2023-10-03 | 3 | W: 2; T: 2
Task 2 | Milestone |  |  | 2023-10-08 | 1 | bar: S
Task 3 | Low Risk |  | 50% | 2023-09-30 | 10
Task 4 | Milestone |  |  | 2023-10-23 | 1 | bar: M
Task 5 | Med Risk |  | 10% | 2023-10-09 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2023-10-09 | 13
Task 2 | On Track |  | 50% | 2023-10-11 | 9
Task 3 | Low Risk |  | 33% | 2023-10-16 | 11
Task 4 | Milestone |  |  | 2023-10-18 | 1 | bar: W
Task 5 |  |  |  | 2023-10-19 | 24
TITLE 3
Task 1 | On Track |  |  | 2023-10-18 | 4
Task 2 | Med Risk |  |  | 2023-10-21 | 14
Task 3 | On Track |  |  | 2023-11-05 | 6
Task 4 | Goal |  |  | 2023-11-09 | 3 | T: 2; F: 2; S: 2
Task 5 | Low Risk |  |  | 2023-10-09 | 19
TITLE 4
Task 1 |  |  |  | 2023-11-12 | 15
Task 2 |  |  |  | 2023-11-26 | 5
Task 3 | Milestone |  |  | 2024-01-07 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2023-10-03 |  |  |  |  | October | [27 empty] | November
Scrolling Increment: | 5 | time axis 2023-10-08 to 2023-12-02
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2023-10-08 to 2023-12-02
TITLE 1
Task 1 | Goal | Name | 25% | 2023-10-03 | 3
Task 2 | Milestone |  |  | 2023-10-08 | 1 | bar: 2023-10-08
Task 3 | Low Risk |  | 50% | 2023-09-30 | 10
Task 4 | Milestone |  |  | 2023-10-23 | 1 | bar: 2023-10-23
Task 5 | Med Risk |  | 10% | 2023-10-09 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2023-10-09 | 13
Task 2 | On Track |  | 50% | 2023-10-11 | 9
Task 3 | Low Risk |  | 33% | 2023-10-16 | 11
Task 4 | Milestone |  |  | 2023-10-18 | 1 | bar: 2023-10-18
Task 5 |  |  |  | 2023-10-19 | 24
TITLE 3
Task 1 | On Track |  |  | 2023-10-18 | 4
Task 2 | Med Risk |  |  | 2023-10-21 | 14
Task 3 | On Track |  |  | 2023-11-05 | 6
Task 4 | Goal |  |  | 2023-11-09 | 3 | 2023-11-09: 2; 2023-11-10: 2; 2023-11-11: 2
Task 5 | Low Risk |  |  | 2023-10-09 | 19
TITLE 4
Task 1 |  |  |  | 2023-11-12 | 15
Task 2 |  |  |  | 2023-11-26 | 5
Task 3 | Milestone |  |  | 2024-01-07 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one